## OpenPDC_WI_9948
CodePlex OpenPDC WorkItems |  | 1. WorkItem 9948 with Change set :77140 in TFS07 in Synchrophasor 2. WorkItem 11954 with Patch Number:11866 in TVACodeLibrary
Description as in IssueTracker |  | It would be useful to have a window that showed a list of the recent exception. Right now, we have everything in the ErrorLog, but in previous versions we had this information available directly from the manager.
Solution Details |  | All exceptions obtained in ErrorLogger in TVA.core will be caught and saved to table ‘ErrorLog’ in the DB. The new Menu item ‘Exception Log’ in ‘Manage’ Menu will list all recent exception caught. A maximum of 2000 records will be available ErrorLog table. After this maximum limit, older records will be overwritten.
Code checkin Date by NeST |  | 2012-03-30
CodePlex's Review comments Date |  | 05-Apr-12 and 11-Apr-12
Sl:No | CodePlex Comment | NeST Comments | More clarification
1 | In the schema updates there was an existing table called "ErrorLog" which was no longer being referenced and you created a new "ExceptionLog" table to hold exception information. We assume that you added a new table since you did not know the consequences of removing ErrorLog, thus you created ExceptionLog - was this assumption correct? | Yes, we added new table as we didn't know the consequences of using the already existing table called ErrorLog.We could see function calls to log into ErrorLog in various modules such as TVA Codelibrary, PMURegistry, Timeseriesframework. The various areas where we saw logging into ErrorLog with the function signature are as below; 1. In TVA Codelibrary: protected virtual bool LogError(string source, string message) 2. In TimeSeriesFramework: public static void LogException(AdoDataConnection connection, string source, Exception ex) 3. In PMURegistry: static void LogException(string source, Exception ex) | We need to clarify if we need to maintain a record limit on ErrorLog ?Or just shown the latest exceptions on the UI, with the entire exceptions in the table.In this case if any other module's use of ErrorLog will not affect the current functionality. [CodePlex's Comment on 11-Apr-12] Restricting error log to 2000 to a rolling rows is perfectly fine and we have no fundamental concerns about references to ErrorLog in other modules based on this logical restriction.
2 | We suggest dropping the new the "ExceptionLog" table and modifying the "ErrorLog" file like so (basically adding your Type field) | This can be done.
3 | Modify code referencing the ExceptionLog to now reference the ErrorLog (changing field reference of DateTime to CreatedOn) | This can be done. Do you need the OpenPDCManger UI's field also to be changed from' Date and Time' to' Created on' | [CodePlex's Comment on 11-Apr-12] No concerns with UI label remaining as-is